## Register
Risk register template
Score = likelihood x impact, each from 1 (low) to 5 (high). See the Scoring guide sheet.
ID | Risk | Category | Likelihood (1-5) | Impact (1-5) | Score | Rating | Owner | Response | Trigger | Status | Next review
1 | Key supplier delivers late | Schedule | 3 | 4 |  |  | Procurement lead | Agree a delivery date with a buffer; identify a second supplier | Supplier misses a checkpoint | Open | 2026-11-16
2 | Scope grows after sign-off | Scope | 4 | 3 |  |  | Project lead | Route every new request through a change log with an owner and an estimate | New request outside the brief | Open | 2026-11-16
3 | Specialist unavailable during build | Resources | 2 | 4 |  |  | Team lead | Book time early; document work so another person can continue | Leave or reassignment announced | Open | 2026-11-16
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
ProjectManagementCenter template. Free to use and adapt. projectmanagement.center/templates

## Scoring guide
Scoring guide
Score | Likelihood | Impact
1 | Very unlikely | Negligible: absorbed without changing the plan
2 | Unlikely | Minor: small delay or cost, handled within the team
3 | Possible | Moderate: visible delay or cost, needs the project lead
4 | Likely | Major: threatens a milestone or the budget, needs the sponsor
5 | Almost certain | Severe: threatens the project goal
Rating | Score range | Typical action
High | 15 to 25 | Act now and review weekly
Medium | 8 to 14 | Plan a response and review every two weeks
Low | 1 to 7 | Watch and review monthly